## OFS - Cr6 (All-in-One)
Work Instruction
Process Name: | GE Vernova Gas Power OFS Hexavalent Chromium (Cr6) Contamination Standard Work Instruction. |  | Process owner: | Ross Conway
Task ID | Work Elements OFS Determining Presence of Cr6 | Who | Start Date | Due (*) Date | Key Points
1 | Determine if there is a potential for Hexavalent Chromium (Cr6) Contamination | Outage Manager | 3 months pre-outage | 1 months pre-outage | • DETERMINE if scope of the outage may be impacted by Hexavalent Chromium (Cr6). • Sampling and management protocols need to be prepared. •refer to Hexavalent Chromium Cr(VI) • Contamination EHS Plan section 4 as basic reference.
2 | • Order / Request applicable Hexavalent Chromium sampling kit and applicable PPE Kit. • Arrange training material for those disassembling potentially affected components. | Outage Manager | 3 months pre-outage | 1 months pre-outage | • Guarantee that the Hex Chrome testing kits are ordered through the tooling centre and that chemicals for qualitative testing are ordered locally. • Consider that training of employees may be needed.
3.1 | Capital Part: Suspect Presence of Hexavalent Chromium through visual indication (yellow, off white powder) | Field Employee (Supervisor, Millwright, FEHS, TFA) | As Outage progresses |  | • Alert / Notify affected employees, contractors and customers about suspicion of potential Hexavalent Chromium. • Note: When Hex Chrome option is added to PIPO, mark appropriate results in the system.
3.2 | Non Capital Part: Suspect Presence of Hexavalent Chromium through visual indication (yellow-ish, OR off-white powder) | Field Employee (Supervisor, Millwright, FEHS, TFA) | As Outage progresses |  | • Alert / Notify affected employees, contractors and customers about suspicion of potential Hexavalent Chromium. • Stop Work. Notify site leadership and EHS Manager. •Follow Step 4
4 | On Site test for parts with visual indications of Hexavalent Chromium | Trained Field Employee (Competent) | As Outage progresses |  | Determine the presence or absence of Hexavalent Chrome by testing guide. For capital parts: If the test results is positive, follow "Shipping Parts" tab. If the test result is negative, continue with normal process. For non-capital parts: If the test result is positive, follow "Decontamination" tab. If the test result is negative, continue outage schedule.
5 | Set up contamination zone as per Hexavalent Chromium guidance | Trained Field Employee (Competent) | As Outage progresses |  | • 'If parts are to be sent with contamination or suspected contamination to GSC/Repair Center, then the parts can be handled with PPE without the need for RPE to be worn. • Refer to "Contamination Zone" Tab.
6 | AND/OR Fill out the PIPO documentation | TFA | As Outage progresses |  | • The updated Parts IN - Parts OUT (PIPO) Process will be used for parts shipped to GSC facilities. • Within the PIPO system, the field employee will identify test results of Cr6 (or part not tested). This system is not yet in place.
Task ID | Work Elements OFS Contamination Zone | Who | Start Date | Due (*) Date | Key Points
1 | Determine Hexavalent Chromium (Cr6) contamination zone boundaries. | TFA / Field EHS | As Outage progresses |  | • Hexavalent Chromium (Cr6) contamination boundaries shall be established in all areas where there is the potential for Hexavalent Chromium (Cr6) exposure. • For an area where contamination has been found -> barrier off 3m/10ft. Barrier should be set-up in a way so that it protects any worker from disturbing the contamination accidentally with a body part or with any equipment. • Area where decontamination activities are being performed -> barrier off >5-10m / >15-30ft. This is to protect other (unprotected) workers on the site not involved from inadvertent exposure to Cr(VI) while the residue is being disturbed. • Other works can continue as normal outside the barriered area. Adjacent workers should be made aware of Cr(VI) being on the worksite and not to cross.
2 | Set-up restricted access to contamination boundaries. | TFA / Field EHS | As Outage progresses |  | • Contamination zones should be barriered off and warning signs posted to restrict access to authorized personnel. • Caution – DO NOT ENTER barrier tape, cones, and signs to define the exclusion zone. • Post signs in area – CAUTION: Cr(VI) Hexavalent Chromium Work Area. • Consider waste disposal bins inside the contaminated area.
3 | Establish PPE requirements for entry into a contamination zone | TFA / Field EHS | As Outage progresses |  | Passive Work: Any task or activity performed in an area with known or potential hexavalent chromium contamination that does not physically disturb contaminated materials or surfaces and is not expected to generate airborne Cr(VI). Passive work does not require RPE. Both Passive and Active work at any level would require all other PPE measures. Reference "PPE Requirements." Active Work: Any task or activity that intentionally or unintentionally physically disturbs hexavalent chromium–containing material or surfaces, with the potential to generate airborne dust, fume, mist, or re‑suspend settled contamination. Active work at any contamination level would require RPE (Respiratory Protection Equipment).
4 | Establish whether Air Monitoring is required in the contamination zone(s). | TFA / Field EHS | As Outage progresses |  | Note: Historically we have IH data that identifies the Airbourne risk is low associated with the handing of Cr6 contaminated parts Outages - Tracking data from outages is challenging due to the intermittent nature of Cr being found (see "Air Monitoring" Tab)
5 | Exiting exclusion zones | TFA / Field EHS | After work is completed |  | • Remove helmet, wipe helmet with damp cloth. • If shoes covers used, place them in a plastic bag for disposal. If not used, clean shoes with a damp cloth . Put the used cloth/rag in a plastic bag for disposal. • Remove the disposable coverall by carefully rolling it inside out. Place it in a plastic bag for disposal. • Remove outer gloves if worn (ie leather gloves) and place them in a plastic bag for disposal. • If needed, keep the respirator on during the processes listed above. • If needed, remove the respirator. If disposable type, place in waste. If reusable type, wipe with a damp cloth, dry, then place in designated containers. • Remove inner gloves (nitrile gloves), taking care to ensure that any potential contamination does not make contact with hand skin.
6 | Personal Hygiene | Craft / Supervisor | After work is completed |  | • After leaving the exclusion zone, proceed directly to the established wash area to thoroughly wash hands/wrists and face or any potential exposed skin with water and soap.
7 | Declassifying contamination zones and removing access restrictions | Industrial Hygienist | As Outage progresses |  | • After leaving the exclusion zone, proceed directly to the established wash area to thoroughly wash hands/wrists and face or any potential exposed skin with water and soap.
Task ID | Work Elements Air Monitoring | Who | Start Date | Due (*) Date | Key Points
1 | Determine which workers are “Exposed” and require personal air monitoring | Site EHS Representee | As Outage progresses |  | The requirements for IH monitoring will be determined for any previously unmonitored tasked.
2 | Fit and deploy personal air monitors for selected workers. | Outage Manager | As Outage progresses |  | For Cr6 routine tasks, monitoring will not be required for outage work due to past data and exposure scenarios.
3 | Send air samples to certified laboratory for analysis | Outage Manager / IH | At the end of each work shift |  | Request fast turn around time from laboratory
Task ID | Work Elements OFS 4 PPE Requirements | Who | Start Date | Due (*) Date | Key Points
1 | Identify specific work tasks that can produce airborne Hexavalent Chromium (Cr6) (e.g., active tasks: grinding, brushing, any activity that will disturb the contaminant and make it airborne). | Field EHS | As outage progress |  | Where active tasks are performed, in addition to hazard specific PPE. Respiratory protection is needed if the residue is be physically disturbed. A half face respirator with P3 or P99/100 particulate filter shall be used. Face mask can be single use disposable type FFP3 (e.g. 3M 8233) or silicon mask type & P3 or P99/100 cartridge.
2 | Issue RPE, if required, to personnel who have had face‑fit testing (clean shaven) before issuing respirators, unless they are issued with PAPR (Powered Air Purifying Respirators) | Site EHS Representative | As outage progress |  | Face fit testing can only carried out by trained personnel.
3 | Supply clean Type 5/6 disposable coveralls to all personnel entering into a contamination zones. | Site EHS Representative | As outage progress |  | Shall be removed and disposed of as contaminated waste before leaving the contamination zone.
4 | Supply single use nitrile gloves to be worn under regular protective gloves. | Site EHS Representative | As outage progress |  | Nitrile gloves shall be: Replaced immediately if torn. Replaced every four hours at a minimum. Removed and disposed of as contaminated waste before leaving the contamination zone.
5 | Overshoes | Site EHS Representative | As outage progress |  | The requirement for overshoes is only required for decontamination activities
6 | All disposable PPE (masks, gloves, coveralls and overshoes) must be removed and disposed of as contaminated waste before leaving the contamination zone. | Craft / Supervisor | As outage progress |  | See "Waste Management" Section
7 | Wash exposed body parts with soap and water immediately after PPE removal | Craft / Supervisor | As outage progress |  | Either set up a washing station/area near the worksite or otherwise ensure that people are cleaning hands/face/neck prior to eating/bathroom or before leaving site.
Task ID | Work Elements OFS 5.1 Decontamination | Who | Start Date | Due (*) Date | Key Points
1 | Identify if the contaminated part is a Capital Part: Proceed to "Shipping Part" tab. Non Capital Part: Proceed with decontamination on site. | TFA/ Supervisor Site EHS / Logistics | As Outage Progress |  | To follow the required steps for capital / non capital parts
2 | Safety Considerations: Review and implement TRA IH TRA - IH16. Make sure that contamination zone was properly set up & proper PPE was selected. While cleaning / decontamination jobs are taking place, make sure a secondary containment, or material is used to prevent liquid contacting the floor or other work surface. | TFA/ Supervisor Site EHS / Craft | As Outage Progress |  | Hexavalent Chromium IH-HRA
3 | Use wet method (WD‑40/Kroil Oil) to clean up the surface. | Craft / Supervisors | As Outage Progress |  | Spray / mist WD40 / Kroil Oil before wiping. Use minimal water to reduce rust risk; avoid WD‑40 under insulation.
4 | After wet cleaning and no visible yellow/off-white powder, consider the part is decontaminated | Supervisors / Logistics | As Outage Progress |  | Visual confirmation is primary clearance criterion for parts.
5 | Dispose all contaminated material as required on the "Waste Management" section . | Craft / Supervisors / Field EHS | As Outage Progress
6 | If parts require further disassembly offsite, mark them accordingly | Logistics / Supervisors / Site EHS | As Outage Progress |  | Contaminated shipments pose risk to service centers/third parties
Task ID | Work Elements OFS 5.2 Tool Management | Who | Start Date | Due (*) Date | Key Points
1 | Tools being used inside contamination zones are considered to be contaminated. Identify, and segregate from clean tools. | Craft / Supervisors | As Outage Progress |  | Contaminated tools should be identified and separated, and they should be decontaminated prior to returning to the tool kit/container.
2 | Tools can be decontaminated by wiping down with WD-40/Kroil Oil. If there is a fire risk, WD40 / Kroil Oil should not be used. In this case, washing down with detergent and water is recommended. | Craft / Supervisors | As Outage Progress
3 | Decontaminated Tools should be return to the main tool container. Any identification/labeling of prior contamination should be removed. | Craft / Supervisors | As Outage Progress |  | After leaving the exclusion zone, proceed directly to the established wash area to thoroughly wash hands/wrist and face or any potential exposed skin with water and soap.
Task ID | Work Elements OFS 6 Waste Management | Who | Start Date | Due (*) Date | Key Points
1 | Label containers at least with specified minimum warning text and chemical symbols | Field EHS | As Outage Progress |  | Classify waste according to local waste codes and inform customer. Comply with any additional site/customer labeling and handling requirements. Dispose all Cr(VI) waste per local legislation.
2 | Identify and collect all contaminated or potentially contaminated disposable materials (PPE, wipes, test kits, reactivs, etc.) | Craft / Supervisors | As Outage Progress |  | Identify all items potentially contaminated with Cr(VI) as special hazardous waste. Includes parts, piping, debris, PPE, plastic sheeting, bags, rags, HEPA vacuum contents.
3 | Store such hazardous waste in defined waste containers provided by the customer. | TFA | As Outage Progress |  | Collect all Cr(VI) waste in adequate, clearly marked containers. Use double‑bagged polyethylene bags placed in drums/containers; mark as “Hexavalent Chromium Cr(VI) Waste”
4 | Transfer to customer defined hazard disposal area | TFA | As Outage Progress
Task ID | Work Elements OFS 7 Shipping | Who | Start Date | Due (*) Date | Key Points
1 | Identify and label parts as tested positive, not tested, tested negative. Package/wrap parts to prevent cross contamination. Place parts inside shipping box. | TFA | As Outage Progress |  | Parts should be packaged and/or wrapped to prevent cross contamination of people and environment (rain etc.) during shipping.
2 | Confirm transportation is managed within regulatory requirements. | TFA | As Outage Progress
3 | Prepare, set package up. Update systems of records (RDM) | TFA | As Outage Progress
4 | Create label and ship components to GSC | CPM / CFM | As Outage Progress |  | Coordinate with receiving repair center as per standard procedures.
Task ID | Work Elements OFS 8 Communications | Who | Start Date | Due (*) Date | Key Points
1 | Inform customer representative of Hexavalent Chrome positive test after being confirmed by the site team. | TFA | As soon as it is tested positive |  | Inform the customer that additional contaminated / hazardous waste will be generated on his site.
2 | Communicate decontamination plan & action plan based on capital / non capital parts. | TFA | As soon as it is tested positive
3 | Communicate contaminated part numbers to CPM. | TFA | As soon as it is tested positive
4 | Communicate contaminated part numbers to GSC shop. | CPM | As soon as it is tested positive
Task ID | Work Elements OFS Training | Who | Start Date | Due (*) Date | Key Points
1 | Provide GE Vernova Hexavalent Chromium (Cr6) Awareness training to all affected field employees | Resource manager | As required by training calendar |  | This will provide a basic level of awareness to employees that potentially can be exposed to Hex Chrome.
2 | Provide any site specific training | Field EHS | As outage progress / needs |  | Train employees on safe methods to execute the task; site specific environmental requirements (waste management), PPE selection and use (site specific), including donning and doffing of specific PPE.
3 | Communicate any change when working with Hex Chrome to the site team. | Resource manager | As required
Note on I54: Edwards1, Mark (GE Vernova): Discussion point for Kaizen is what if customer is unable to lower levels to beneath 200 - ITO contract language???