## Agenda (hidden)
Typical Kaizen Event Agenda (ideally face-to-face; can also be done virtually) |  |  | RETURN TO USER GUIDE
Adjust this to meet the specific needs of your event. Standard elements of training, daily leader's meetings, execution of actions/changes for Monday, and report out should ALWAYS be included.
USA EST | Day 1 Monday | Day 2 Tuesday | Day 3 Wednesday | Day 4 Thursday | Day 5 Friday
| Introductions, Training, Current State | Analyze Current State, Create Future State, Develop Action Plan | Build, Test, Refine Solutions | Implement Solutions Plan to Operationalize & Sustain Lessons Learned | Present Results & Celebrate
8:00 | Kickoff, Introductions & Safety | Recap & Plan for the Day Complete Safety & Ergo Assessments | Recap & Plan for the Day Complete Safety & Ergo Assessments | Recap & Plan for the Day Complete Safety & Ergo Assessments | Recap & Plan for the Day Complete Safety & Ergo Assessments
8:30 | Lean Training: Creating a Standard | Lean Training | Execute Action Plan Build, Test, Refine Solutions | Execute Action Plan Implement Final Solution | Participant Survey Final Presentation Prep
9:00
9:30
10:00
10:30 |  | Analyze Current State Waste & Problem Identification Root Cause Determination Solution Generation Prioritization
11:00 |  |  |  |  | Report Out
11:30 |  |  |  |  | Kaizen Self Assessment
12:00 | Lunch | Lunch | Lunch | Lunch
12:30
13:00 | Current State- Continue Reason Matrix: What has been tried | Future State Creation Develop Action Plan... What changes for Monday? | Execute Action Plan Build, Test, Refine Solutions | Plan to Operationalize & Sustain Post-Kaizen Action Plan Lessons Learned Team Picture
13:30
14:00
14:30
15:00
15:30
16:00 | Daily Debrief (Optional) | Daily Debrief (Optional) | Daily Debrief (Optional)
16:30 | Daily Leaders Meeting | Daily Leaders Meeting | Daily Leaders Meeting | Daily Leaders Meeting
17:00

## Daily Targets (hidden)
Daily Target Sheet | RETURN TO USER GUIDE
Lists the metrics that are targeted to be impacted during the event and is updated daily and changes are being made.
SQDC | Business Metric | Unit of Measure | Baseline | Target | Day 1 Result | Day 2 Result | Day 3 Result | Day 4 Result | Final Result | % Improved from start
#REF! |  |  | #REF! | #REF!
#REF! |  |  | #REF! | #REF!
#REF! |  |  | #REF! | #REF!
#REF! |  |  | #REF! | #REF!
#REF! |  |  | #REF! | #REF!
Reference: Kaizen Impact Standard Target Sheet
This a reference library of metrics that are typically good leading indicators for impact across SQDC + Cash and can be used to aid when selecting the target metrics for your Kaizen.
SQDC+Cash | Business Metrics | Unit of Measure | Definition |  |  |  | Examples
Safety | Safety improvement | Count (#) | Number of improvements made to the safety of process. |  |  |  | - Trip hazard eliminated in a manufacturing cell or office environment - Ergonomics improvement in an office environment - Cyber security risk reduction - Work/life balance and mental health improvement
| Compliance risk reduction | Count (#) | Number of compliance risks reduced in the process.This may be related to violations against internal GE policies or regulatory requirements. |  |  |  | - Violations against company policy for Environment, Health, and Safety (EHS) violations - Occupational Safety and Health Administration (OSHA) violations - Number of data compliance violations (e.g. HIPAA, GDPR)
Quality | Scrap reduction | Dollar ($) | Scrap is the dollar value of unusable material that is left over after a product has been manufactured. |  |  |  | - Scrap due to material non-conformances where the part cannot be repaired - Scrap due to engineering part obsolescence
| Defect reduction | Count (#) | A defect is a process non-conformance that impacts the quality of a final product. That product can be physical or transactional. May be measured in terms of "defects per million" or number of quality improvements for a process. |  |  |  | - Number of manufacturing defects (i.e. part tolerances over allowable limit) - Number of misclassifications for field quality cases - Number of late manual journal entries (MJE) - Number of technology outages or incidents (ServiceNow)
| First pass yield improvement | Percentage (%) | First pass yield (FPY) is defined as the number of units coming out of a process divided by the number of units going into that process over a specified period of time. This metric measures the % improvement of FPY. |  |  |  | - FPY of the tact weld operation in a manufacturing plant - FPY of the material review for the Board of Directors presentation - FPY of internal deliverables within a transactional environment (reports, QMI submissions, quarter end items, etc.)
Delivery | Volume output | Pieces/day | Volume output, on a piece part basis, is the total number of pieces / units produced over a set period of time. This metric will be reported on a daily basis.
| Volume output (revenue) | Dollar ($) | Volume output, on a revenue basis, is the $ amount (revenue generating) of the total number of pieces / units produced over a set period of time.
| Lead-time reduction | Count (# Days) | Lead time is measured from the customer perspective and is defined as the time from when the customer makes a request to the time when they receive something. This metric measures the number of lead time days reduced in a value stream. |  |  |  | - Lead time to deliver a gas turbine to the customer - Lead time from when a purchase order is placed to when the material arrives - Lead time for finance monthly close - Lead time for a wing-to-wing Sales, Inventory & Operations Planning cycle
| Stockout reduction | Count (# Stockouts) | A stockout is an event that causes inventory to be exhausted. It occurs when customer demand for a product exceeds the amount of inventory kept on-hand. This metric measures the reduction in stockouts of a process / operation.
Delivery (or Cost) | Cycle time (or labor hour) reduction | # of Hours | Cycle time is measured from the internal process perspective, and is the hours or labor hours reduced within a process step - including value add time and non-value added time. Especially relevant for transactional process that may not be repeatable to show productivity gains. |  |  |  | - Number of hours required for heat treatment manufacturing operation - Number of hours to develop request-for-quotation or complete supplier onboarding - Number of hours for FP&A activity (monthly estimate consolidation, forecasting, or other pacing activities) - Number of Service Level Agreement (SLA) hours
Cost | Space reduction | Square foot (sq.ft.) | The amount of space required to house a process / operation.
| Distance traveled | Feet (ft.) | The amount of physical distance traveled by an operator to perform a process / operation..
| Productivity (units/human hours) | Percentage (%) | Productivity measures the efficiency of production as an output per unit of input. This metric measures productivity of units produced compared to human hours applied.
Cash | Working capital improvement | Dollar ($) | Improvements resulting in positive cash flow impact on working capital, or operating liquidity. This metric will be reported at the net working capital improvement level, but include the following sub-areas: inventory reduction, accounts receivable reduction, accounts payable improvement |  |  |  | - Reduction in Inventory - Reduction in Account Receivables (AR) - Increase in Account Payables (AP) - Increase in Progress Collections
Note on E5: Automatically linked to Charter

## Trystorming (hidden)
Daily Trystorm Tracking |  |  | RETURN TO USER GUIDE
A tool to encourage and track Trystorming throughout the event to achieve the Kaizen objectives
% Complete
# | Gap to be Addressed | Solution to Try | Experiment | Anticipated Result | 25% | 50% | 75% | 100% | Actual Result | Follow Up Actions
1
2
3
4
5
6
7
8
9
10

## Daily Summary (hidden)
Daily Leader's Meeting 4-Block | RETURN TO USER GUIDE
Assesses progress at the end of each day, specifically identifying any immediate actions required to continue making progress towards the Kaizen objective. On Friday, capture the team's overall lessons learned to incorporate into the final event report out.
Monday |  | Tuesday
Done Today | Tomorrow's Tasks | Done Today | Tomorrow's Tasks
Lessons Learned / Ah Ha Moments | Concerns / Changes / Help Needed | Lessons Learned / Ah Ha Moments | Concerns / Changes / Help Needed
Wednesday |  | Thursday
Done Today | Tomorrow's Tasks | Done Today | Tomorrow's Tasks
Lessons Learned / Ah Ha Moments | Concerns / Changes / Help Needed | Lessons Learned / Ah Ha Moments | Concerns / Changes / Help Needed
Friday
Lessons Learned - Process/Business/Organization | Lessons Learned - Lean Tools/Methodology/Culture

## Kaizen Newspaper (hidden)
Post-Kaizen Action Plan / Kaizen Newspaper |  |  | RETURN TO USER GUIDE
Lists any remaining actions to be completed, which should all have a due date within 30 days of event end.
Planned Date
Action Step | Owner | Assist |  | K+1 | K+2 | K+3 | K+4 | Comments
Item 1 | Jane | Joe | Feb 5 | X
Item 2 | Bruce | Cindy | Feb 5 Feb 12 |  | X
Item 3 | Jane | Cindy | Feb 11 | X
Item 4 | Jane | Sam | Feb 5 Feb 20 |  | X | X
Item 5 | Cindy | John | Feb 20
Item 6 | Jane | Sam | Feb 22
QMS - Have all Procedures, Work Instructions or Guidance documents associated with the process been identified, reviewed and updated to match the post-kaizen condition? | Jane | Sam | Feb 22
QMS - Have changes to Procedures, Work Instructions or Guidance documents been communicated and where applicable training given. | Jane | Sam | Feb 22
Instructions:
K+1, 2, 3, 4 indicates the # weeks post-kaizen. You can replace these with dates, if you like. All actions should ideally be completed within 4 weeks of the kaizen event
Do NOT erase dates once finalized. Strike-through and show new date.
Green is "on track" or "complete"
Red is "at very high risk needing attention" or "Past due"
Grey indicates future actions not yet started for the blocks on the Gantt chart
The X indicates that the action step is active or in progress in that week.
An X before the colored in sections indicate you started early.
An X after the colored in sections indicates you are late and are still working that step.

## Post-Kaizen Daily Mgt (hidden)
Post-Kaizen Daily Management | [34 empty] | RETURN TO USER GUIDE
This 8-Block Board should be built on Day 4 or 5 of the Kaizen Event and is used for 90 days following the event, with the Genba team, to ensure sustainment of the changes from your Kaizen. Ideally, this board is implemented (printed and hand written) physically, at Genba, and the team huddles daily (or at the cadence at which the process runs).
Problem Statement | [34 empty] | Run Chart
| This updates from the Charter tab in this Playbook. | [34 empty] | Metric (Unit of Measure) | Scale -->
#REF!
100
95
90
85
80
75
70
65
60
55
50
45
40
35
30
25
20
15
10
5
[38 empty] | Day --> | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Metrics | [34 empty] | Issue Pareto
The first 7 columns of this table updates from the Daily Target Sheet tab in this Playbook.
[36 empty] | Frequency of Occurrence (Date of Occurrence) | 20
19
18
17
16
| SQDC |  | Business Metric |  |  |  | Unit of Measure |  |  |  | Baseline |  |  | Target |  |  | Kaizen Result |  |  | % Improved from start |  |  | 30 Day Result |  |  | 60 Day Result |  |  | 90 Day Result |  |  | % Improved from start |  |  |  |  | 15
14
| #REF! |  | 0 |  |  |  | 0 |  |  |  | #REF! |  |  | #REF! |  |  | 0 |  |  | 0% | [16 empty] | 13
| #REF! |  | 0 |  |  |  | 0 |  |  |  | #REF! |  |  | #REF! |  |  | 0 |  |  | 0% | [16 empty] | 12
| #REF! |  | 0 |  |  |  | 0 |  |  |  | #REF! |  |  | #REF! |  |  | 0 |  |  | 0% | [16 empty] | 11
| #REF! |  | 0 |  |  |  | 0 |  |  |  | #REF! |  |  | #REF! |  |  | 0 |  |  | 0% | [16 empty] | 10
| #REF! |  | 0 |  |  |  | 0 |  |  |  | #REF! |  |  | #REF! |  |  | 0 |  |  | 0% | [16 empty] | 9
8
7
6
5
[37 empty] | 4 |  |  | 2022-03-05
[37 empty] | 3 |  |  | 2022-03-05
[37 empty] | 2 |  |  | 2022-03-04
[37 empty] | 1 | 2022-02-02 |  | 2022-03-03
[38 empty] | Issue Description #1 |  | Issue Description #2
Issue
Attendance Tracker | [34 empty] | Countermeasures
Present
Not Present*
Weekend, holiday, or meeting not held
|  |  |  | Month/Year: _______________ |  |  |  |  | 2022-02-22 | [7 empty] | * If on PTO, fill day with red, but type in "PTO". In an Event, type "E"
Day
| Name |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 |  | Date ID'ed |  | Issue Description | [7 empty] | Status |  | Next Action | [6 empty] | Owner |  |  | Target Date |  | On Track |  | Comments, last update date
[36 empty] | 2022-03-05 |  | Issue Description #2 | [7 empty] | ◑ |  | Action #1 | [6 empty] | Name |  |  | 2022-03-09 |  | No
Training Matrix | [34 empty] | Post-Kaizen Daily Management Standard Work
[37 empty] | Standard Work - Business Process | [13 empty] | Desired Outcome |  |  | Mgmt & Sustainment of Kaizen Changes | [6 empty] | Process
|  |  |  | Day 19: Date of Last Update:; Day 25: 2022-01-12 | [26 empty] | Rev
[51 empty] | Location |  |  | at Genba | [6 empty] | Created
Author
[37 empty] | # | Work Content | [10 empty] | Time (Min)
[37 empty] | 1 | Review the What & Why and take attendance | [10 empty] | 1
|  |  |  | Day 6: Name 1; Day 8: Name 2; Day 10: Name 3 |  |  | 2 | Review the Problem Statement from Kaizen and Outcome Measure Run Chart | [10 empty] | 1
|  | Ref |  | Day 1: Item/Process Step |  |  | 3 | Review Standard Work Layout | [10 empty] | 1
|  | 1 |  | Day 1: RCA SW
|  |  |  | Day 1: Submission |  |  | 4 | Review Training Matrix, noting ahead & behind | [10 empty] | 2
|  | 2 |  | Day 1: Validation
[37 empty] | 5 | Review Run Chart. Did we perform the new Standard Work Layout? | [10 empty] | 2
[37 empty] | 6 | Pareto Where and Why the Standard Work Layout was not achieved | [10 empty] | 4
[37 empty] | 7 | Capture countermeasures and actions | [10 empty] | 4
8
9
10
[38 empty] | Total Time (Min) | [10 empty] | 15

## Certificate (hidden)
Certificate of Participation |  | RETURN TO USER GUIDE
Optionally presented to each Kaizen team member, individually by the Executive Sponsor of the Kaizen Event, often along with a group photo or other nominal gift in appreciation of their participation.
PLEASE CONTINUE TO PRACTICE KAIZEN, CONTINUOUSLY
Event Title Here
Org
Name
FirstName LastName
has successfully participated in a Kaizen Event practicing
List Kaizen Tool(s) Applied Here (Standard Work, Kanban, 3P, etc.)
from DD-MON-YYYY to DD-MON-YYYY
Executive Sponsor Name Here
Title
Business

## Report Out (hidden)
RETURN TO USER GUIDE

## Closure (hidden)
RETURN TO USER GUIDE
KAIZEN | #REF! |  |  |  | Run Kaizen Event
Kaizen | Due | Date | Accountable | Roles | Task
Timing | Date | Completed | Role | Engaged
During kaizen | #REF! |  | PO | PO, TL | Standard work is completed, posted and implemented
| #REF! |  | PO | PO, TL | Communication plan is developed and shared
| #REF! |  | PO | PO, TL | Training plan created
| #REF! |  | PO | PO, TL | Post-Kaizen Action Plan (newspaper) complete and all items due within 30 days
| #REF! |  | PO | PO, TL | Visual management established and operational
| #REF! |  | PO | PO, TL | Target state met
| #REF! |  | PO | PO, TL | Weekly meeting for next 3 weeks scheduled with PO
| #REF! |  | PO | PO, TL | Participant survey completed (optional)
| #REF! |  | PO | ES, PO, F | 30/60/90 Schedule sustainment calls after 30 days, 60 days, 90 days
| #REF! |  | PO | ES, PO, F | Key Roles Assessment completed
+1 week | #REF! |  | PO | PO | Post-Kaizen Action Plan, Communication Plan, Training Plan Status
| #REF! |  | PO | PO | Validate performance against target state
| #REF! |  | PO | PO, ES, F | Escalate to ES and F, if red
| #REF! |  | PO | PO, TL | QMS checks - Have all Procedures, Work Instructions or Guidance documents associated to the process been identified and reviewed. (Please List)
+2 weeks | #REF! |  | PO | PO | Post-Kaizen Action Plan, Communication Plan, Training Plan Status
| #REF! |  | PO | PO | Validate performance against target state
| #REF! |  | PO | PO, ES, F | Escalate to ES and F, if red
+3 weeks | #REF! |  | PO | PO | Post-Kaizen Action Plan, Communication Plan, Training Plan Status
| #REF! |  | PO | PO | Validate performance against target state
| #REF! |  | PO | PO, ES, F | Escalate to ES and F, if red
+30 days | #REF! |  | PO | PO | Verify process performance (what's working/not working). Target state from event has been achieved.
| #REF! |  | PO | PO, F | Problem Solving cadence in place to continuously improve the process performance
| #REF! |  | PO | PO | Review Standard Work - is it being followed? If not, why?
| #REF! |  | PO | PO, F | Complete a waste walk. Are there additional ideas to for improvement?
| #REF! |  | PO | ES, PO, F | Verify leader(s) are performing their leader standard work. (Going to genba, helping the team break down barriers, and supporting the Lean Management System)
| #REF! |  | PO | ES, PO, F | Verify the visual management system is giving responsive feedback and driving changes in behavior when trending in the wrong direction.
| #REF! |  | PO | ES, PO, F | Escalate if red/help needed
+60 days | #REF! |  | PO | PO | Verify process performance (what's working/not working). Target state from event has been achieved.
| #REF! |  | PO | PO, F | Problem Solving cadence in place to continuously improve the process performance
| #REF! |  | PO | PO | Review Standard Work - is it being followed? If not, why?
| #REF! |  | PO | PO, F | Complete a waste walk. Are there additional ideas to for improvement?
| #REF! |  | PO | ES, PO, F | Verify leader(s) are performing their leader standard work. (Going to genba, helping the team break down barriers, and supporting the Lean Management System)
| #REF! |  | PO | ES, PO, F | Verify the visual management system is giving responsive feedback and driving changes in behavior when trending in the wrong direction.
| #REF! |  | PO | ES, PO, F | Escalate if red/help needed
+90 days | #REF! |  | PO | PO | Verify process performance (what's working/not working). Target state from event has been achieved.
| #REF! |  | PO | PO, F | Problem Solving cadence in place to continuously improve the process performance
| #REF! |  | PO | PO | Review Standard Work - is it being followed? If not, why?
| #REF! |  | PO | PO, F | Complete a waste walk. Are there additional ideas to for improvement?
| #REF! |  | PO | ES, PO, F | Verify leader(s) are performing their leader standard work. (Going to genba, helping the team break down barriers, and supporting the Lean Management System)
| #REF! |  | PO | ES, PO, F | Verify the visual management system is giving responsive feedback and driving changes in behavior when trending in the wrong direction.
| #REF! |  | PO | ES, PO, F | Escalate if red/help needed
Note on B2: Dates will auto-populate from CHARTER TEMPLATE

## Participant Survey (hidden)
Kaizen Event Participant Survey | [5 empty] | RETURN TO USER GUIDE
An optional survey to be given to participants on the last day of the event and the results reviewed for continuous improvement opportunities.
| Event Name: |  |  |  | Date:
# | Question | Strongly Agree | Agree | Disagree | Strongly Disagree | Comments
1 | I felt empowered to make changes to the process this week.
2 | I am satisfied with the facilitator's performance in leading/coaching the event.
3 | I am satisfied with the results impact of this week's efforts.
4 | I am pleased with this week as a personal learning experience.
5 | The training provided during the event was clear and meaningful.
6 | I am interested in participating in another Kaizen event in the future.
7 | I feel this event had appropriate leadership support (Executive Sponsonr & Process Owner).
8 | I have a good undertanding of the Lean tools applied during this event.
9 | The preparation done prior to the event was adequate and appropriate.
10 | I understand why this event was done and its strategic importance to the business.
Other Comments or Questions:
Thank you for your Feedback!!

## Key Role Survey (hidden)
Key Roles Survey |  |  |  | RETURN TO USER GUIDE
A guide for conducting a post-Kaizen debrief / reflection session with the Executive Sponsor, Process Owner, Facilitator and Team Leader.
It is recommended to do after the final report out, ideally within 3 business days.
# | Question | Yes | No | Comments
1 | Was training completed and relevant to the week?
2 | Were participants fully committed to the week? (i.e. people not stepping in and out)
3 | Was the prep work for the event sufficient and complete?
4 | Did the Executive Sponsor appropriately kickoff the event?
5 | Were the daily debriefs well attended including Executive Sponsor and stakeholders?
6 | Was the team trystorming by Wednesday?
7 | Were solutions setup for sustainment in the week? (i.e. Standard work written, Daily Mgmt leveraged)
8 | Was the final Report Out well attended including Executive Sponsor and stakeholders?
9 | Does the Post-Kaizen Action Plan have less than 5 items and all due within 30 days?
10 | Were leaders in the kickoff, debriefs, and the report out modeling the GE Leadership Behaviors?
11 | Were the Kaizen metric targets achieved in the week?
Worked Well (+) |  |  | Change for Next Time (∆)

## Reason Matrix (hidden)
Parts Delay Reasons
In 2024, 79% of Planned Outages received less than 100% of parts before scheduled start. (CSA Planned Only)
Reason | Why? | What's Been Tried | New Opportunities | Next Steps
Unrealistic metric? Is it necessary to have 100% of parts arrive before scheduled start?
Lack of visibility
Supplier issues
Unclear roles & responsibilities
Bandwidth issue
Lead time issues
Too many people involved in tracking/acquiring parts
Parts ordered too late
Inventory re-allocated to prioritized outage
Tableau Server
https://tableau.cloud.digital.ge.com/#/views/xPGSCSOutagesDashboard/L1RootCauses?:iid=3

## Template
XXX (Project Name)
Idea Approved (Stage 0): | Not Approved
Total Hours to Implement Initiative
VO Owner: | Jim Vono |  | Incremental Systems Investment Required: | No
Approved On: |  |  | Approved On:
Team |  | Average Workweek | Process Step L2 | Average Time (min/wk) | Current FTE (As of May 2026) | Total NVA Eliminated Time per Year (hrs) | Functional Owner | Approved On:
Personna 1 | Current State | 60 | xxxx | 0 | 0 | 0
| Future State | 60 | xxxx | 0 | 0 | 0
|  |  | Persona 1 Capacity Gain / NVA Eliminated |  |  | 0
Personna 2 | Current State | 60 | xxxx | 0 | 0 | 0
| Future State | 60 | xxxx | 0 | 0 | 0
|  |  | Persona 2 Capacity gain / NVA Eliminated |  |  | 0
Personna 3 | Current State | 60 | xxx | 0 | 0 | 0
| Future State | 60 | xxx | 0 | 0 | 0
|  |  | Persona 3 Capacity Gain / NVA Eliminated |  |  | 0
|  |  | Total |  |  | 0
Support details
Persona 1 Activity | CURRENT STATE |  | FUTURE STATE
xxx | 0 |  | 0
xxx | 0 |  | 0
xxx | 0 |  | 0
xxx | 0 |  | 0
xxx | 0 |  | 0
Persona 1 Total | 0 |  | 0
Persona 2 Activity | CURRENT STATE |  | FUTURE STATE
Sub-Task 1 |  |  | 0
Sub-Task 2
Sub-Task 3
Sub-Task 4
Sub-Task 5
Persona 2 Total | 0 |  | 0
Persona 3 Activity | CURRENT STATE |  | FUTURE STATE
Sub-Task 1
Sub-Task 2
Sub-Task 3
Sub-Task 4
Sub-Task 5
Persona 3 Total | 0 |  | 0
WITH CUT-IN TIMING | % of year benefit
TOTAL 2026 benefit |  |  | 0 | NVA hrs
TOTAL 2027 benefit |  |  | 0 | NVA hrs
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## PCA (hidden)
PCA Tool Enhancements
Idea Approved (Stage 0): | Not Approved
Total Hours to Implement Initiative
VO Owner: | Jim Vono |  | Incremental Systems Investment Required: | Yes
Approved On: |  |  | Approved On:
Team |  | Average Workweek | Process Step L2 | Average Time (min/wk) | Current FTE (As of June 2024) | Total NVA Eliminated Time per Year (hrs) | Functional Owner | Approved On:
PCA | Current State |  | OPU Preparation | 210 | 80 | 14560
| Future State |  | OPU consolidation tool + CDSi & PPR merge | 85 | 80 | 5893.3333
|  |  | Persona 1 Capacity Gain / NVA Eliminated |  |  | 8666.6667
| Current State |  | Primavera Schedule Baseline Optimized | 923.0769 | 80 | 64000
| Future State |  | Primavera Schedule Baseline Optimized (AI) | 818 | 80 | 56714.6667
|  |  | Persona 2 Capacity gain / NVA Eliminated |  |  | 7285.3333
| Current State |  | OPU Email | 95 | 80 | 6586.6667
| Future State |  | OPU Email (AI) | 40 | 80 | 2773.3333
|  |  | Persona 2 Capacity gain / NVA Eliminated |  |  | 3813.3333
| Current State |  | PCA Excel Audit File Issue | 92.31 | 80 | 6400.16
| Future State |  | IRFPCA Audit | 62.11 | 80 | 4306.2933
|  |  | Persona 3 Capacity Gain / NVA Eliminated |  |  | 2093.8667
| Current State |  | Initial Primavera Schedule Draft Creation 7F | 57.6923 | 80 | 4000
| Future State |  | SMT for 7F (Automatized initial P6 Schedule Creation) | 22 | 80 | 1525.3333
|  |  | Persona 3 Capacity Gain / NVA Eliminated |  |  | 2474.6667
| Current State |  | Creation of Initial Task list for Field Time | 20 | 80 | 1386.6667
| Future State |  | Guided Time Entry Tool sync with P6 (all Regions) | 5 | 80 | 346.6667
|  |  | Persona 3 Capacity Gain / NVA Eliminated |  |  | 1040
|  |  | Total |  |  | 25373.8667
Support details
Persona 1 Activity | CURRENT STATE |  | FUTURE STATE
Merge CDSi with PPR | 60 |  | 30
Check previous week and consolidate | 150 |  | 55
| 0 |  | 0
Persona 1 Total | 210 |  | 85
Persona 2 Activity | CURRENT STATE |  | FUTURE STATE
Baseline optimization (avg 20 events per year) | 923.0769 |  | 818
Persona 2 Total | 923.0769 |  | 818
Persona 3 Activity | CURRENT STATE |  | FUTURE STATE
PCA Audit | 92.31 |  | 62.11
Persona 3 Total | 92.31 |  | 62.11
WITH CUT-IN TIMING | % of year benefit
TOTAL 2026 benefit | 0.5 |  | 12686.9333 | NVA hrs
TOTAL 2027 benefit | 0.5 |  | 12686.9333 | NVA hrs
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!