One Field Services  |  Technical Training Delivery

NATIONAL CTE PROGRAM FRAMEWORK

The recipe for taking the entry-level craft mechanic program national

| Owner | Linda Nelson |
| --- | --- |
| Sponsor | Jim Rosen |
| Version | 2 — August 24, 2026 (supersedes the July 10 four-bucket working doc) |
| Status | Working plan. Details will change as partners, districts, and funding firm up. That is expected and fine. |
| Handling | GE Vernova internal. |

# HOW TO READ THIS DOC

This is a recipe, not a strategy deck. It is built to be followed step by step.

The plan has three layers, and they connect top to bottom:

- The Framework (this doc) is the what — the five pillars of the national program and the plan for each. Anyone should be able to open this and understand how we get from a Houston pilot to a self-funding national program.

- Action Plan items are the how and when — a program-sized AP item per pillar (six in all; Pillar 2 carries two, since instructors and equipment are separate multi-month programs), each with a single owner that goes through the normal review chain. Each sits nested under its pillar, marked as an Action Plan Item, with its step-by-step child beats underneath. The children are where the real dates and hand-offs live, and they follow the tracker's usual arc: Define, Develop, Pilot, Sustain.

- ORiON actions are the ground-level tasks that support an AP child when one needs breaking down further. The small, near-term stuff (confirm a policy, hand off a document, book a room) lives here, not as its own AP item.

Each pillar below has: what it covers, where it stands today, the plan, and the AP item it proposes with its child beats. When a decision lands, write it in and date it. When something blocks you, flag it and pull Jim in.

The destination A national entry-level craft mechanic program that runs at partner districts and tech schools, is backed by an industry-recognized certification, and pays for itself through grants and credentialing revenue rather than depending on training budget year to year. Target scale is roughly 80 to 90 completions a year, enough to match field attrition.

# WHERE WE ARE TODAY

This matters because the recipe assumes it. As of late August 2026:

- The pilot works. The summer Houston cohort validated the model: 7 students completed, 6 signed offers (scoring 81 to 93), one washed out on attendance before any hire cost was incurred.

- The next cohort is real and funded by someone else. 18 district-funded students start September 1.

- Leadership is pulling, not pushing. Jim Vono and Cal are aligned on exploring the national build. What we have is permission to keep going, not a budget commitment. The framework is partly how we earn the budget conversation.

- The load is on a few people. Linda is carrying partnerships, districts, vendor, EHS fallback, CapEx, and certification at once. Roy is primary on the five-week program and standing up CTE hands-on and the only holder of the combustion removal sequence. This is a plan that has to be executed without adding much headcount, which shapes several pillars below.

# PILLAR 1 — EXTERNAL PARTNERSHIPS

What this covers: Every outside organization at the table and what tier they sit in. NRG, San Jacinto College, HCC, independent school districts, and whoever comes next. This pillar answers: who are we working with, what does each one give us, what do they get, and what can Linda commit to without escalating.

Where it stands: Partnerships are lighting up faster than the guardrails are being set. The recurring pattern across San Jac, NRG, and ARC is that Linda and Jim keep ending up in partner meetings slightly above their remit, and GE Vernova brand and legal approval keep being the thing that gates progress. The framework fixes this by making the tiers and the commitment limits explicit before the next meeting, not after.

### The plan — partner tiers

| Tier | Who | What they provide | What they get |
| --- | --- | --- | --- |
| Tier 1 — Corporate | NRG, other employers | Hiring demand, possible funding, credibility | Trained pipeline, first look at graduates |
| Tier 2 — Community / Tech College | San Jacinto, HCC | Facilities, accreditation pathway, co-branding | Program content access (tiered), shared enrollment |
| Tier 3 — School District (ISD) | Local + national districts | Students, district funding, CTE pathway eligibility | Turnkey curriculum, equipment guidance, certification |

The guardrail that keeps biting us: what content and IP each tier can actually access is not settled, and it is the live dependency before most partner meetings. The content/IP split itself lives in Pillar 2 (How We Do It); the decision about who gets what is a partnership decision. Cross-reference kept deliberately.

ACTION PLAN ITEM Formalize the CTE Partnership & Tier Framework Owner: Linda. The program-sized deliverable: a defined tier model (who sits where, what each tier gives and gets), the commitment limits that say what Linda can agree to without escalation, and the IP-sharing rules that make those limits real. This turns partnership from meeting-by-meeting improvisation into a standard the whole program runs on. Child beats: Define — draft the tier model and the commitment-limit guardrails, before the next NRG or district meeting. Develop — settle the standing legal support path and the per-tier IP-sharing rules with legal. Pilot — run the San Jac and NRG agreements through the new framework and adjust. Sustain — document the tier framework as standard work; new partners get slotted, not renegotiated from scratch. Near-term ORiON actions: resolve the San Jac NDA redlines and signatory (already live); confirm the standing legal resource (Stephen vs. someone from legal who works with Alvaro on commercial projects — Cal's call, gates every agreement); connect Caroline (HR) with Linda on applicability outside NAM.

# PILLAR 2 — HOW WE ACTUALLY DO IT

What this covers: The two things the national model actually runs on — instructors and equipment — plus the content and curriculum that fills them, plus the methods we use to get students to competency when we are not standing in the HLC high bay. This is the biggest and most detailed pillar because it is where the program physically happens.

Where it stands: The summer cohort proved it can be done in Houston. The national question is different: how do you deliver hands-on competency at a district you don't staff and don't own, without shipping your best instructors around the country full time.

### 2a. Content and curriculum

- What's ours to share vs. GE-proprietary is still the unsettled guardrail. Base fundamentals — precision measurement, safety, core mechanic skills — are broadly shareable. GE-specific tooling procedures and OFS workflows are not. This split needs to be written down, because it determines what a Tier 2 or Tier 3 partner can be handed.

- Curriculum backbone is Amatrol modules plus hands-on blocks. Students complete the relevant Amatrol module and a ten-question assessment before each hands-on block. That prerequisite model is the standardizable core — it travels to any district.

- Content is porting into Xyleme. This is the mechanism that makes curriculum deployable at distance rather than living in one instructor's head.

### 2b. The methods to reach competency

This is the part that makes national possible. Four methods, used in blend depending on the partner:

| Method | What it is | Best for | Watch-out |
| --- | --- | --- | --- |
| VR / simulation | Exalter or in-house simulation of turbine work | Districts with no physical assets; early skill-building | In-house needs a written storyboard that doesn't exist yet |
| Stranded / decommissioned assets | Real turbine hardware pulled from decommissioned sites | Districts near a decommissioned asset; realism | PCB scrubbing, book value, custody, transport, refurb unresolved |
| Mobile labs | Equipment that travels to the district for the hands-on window | Districts without permanent space | Cost and logistics per deployment |
| Blended | Amatrol + VR locally, hands-on in a 2-week block | The default national model | Depends on the 2-week block being deliverable locally |

The current working model: decouple from HLC. Push the two hands-on weeks out to districts and tech schools using a standardized Amatrol / Exalter / in-house pick-list, so students are only on-site for two weeks. Everything else is delivered locally or virtually.

### 2c. Instructors

- National delivery cannot lean on borrowed instructors. The instinct to over-hire and peel some off was tested and rejected — using existing team members already here with no competing priorities is the better answer. That logic scales: the national model needs a train-the-trainer path, not a borrowed-instructor pipeline.

- Zed is the train-the-trainer candidate. Linda is already developing him — into staff meetings and the Xyleme/Atlas conversations, and planning him as train-the-trainer lead if Midland or PA come through. Ahead of the role formally existing, which is the right instinct.

- Roy is the single point of failure to design around. He's primary on the five-week program, standing up CTE hands-on, and the only holder of the combustion removal sequence. The national plan has to reduce that concentration, not add to it.

### 2d. Equipment

- Standardized ISD kit specs, not location-by-location patchwork. Both Jim V and Cal want this. The national model needs one defined equipment pick-list a district can buy or be given, not a bespoke build each time.

- Decommissioned assets are contested. Jim V wants a request deck for a 7F Users Group asset ask in Salt Lake City. Cal is skeptical about deploying decommissioned assets to external sites and would rather pull good ones back to HLC. Unresolved, and it affects the stranded-assets method.

This pillar carries two program-sized efforts, so it gets two AP items — one builds the capacity to deliver (instructors), the other builds the means to deliver (equipment and the content that travels). They run in parallel.

ACTION PLAN ITEM Build the National CTE Instructor Capacity Model Owner: Linda / Harry. A train-the-trainer path that lets the program staff hands-on delivery at districts without shipping HLC's core instructors around the country, and that removes the single-points-of-failure the pilot exposed. Child beats: Define — map the instructor roles the national model needs and the competencies each requires. Develop — build the train-the-trainer curriculum; formalize the role that doesn't officially exist yet. Pilot — run Zed through it as the first train-the-trainer lead (tied to Midland/PA if they come through). Sustain — standardize so each new district can grow its own qualified deliverer. Near-term ORiON actions: get Zed into staff meetings and the Xyleme/Atlas conversations; capture the combustion removal sequence from Roy and hand it to Philip.

ACTION PLAN ITEM Develop the Standardized ISD Equipment & Content Program Owner: Linda / Roy. One defined, buyable-or-grant-fundable equipment kit spec a district can adopt without a bespoke build, the content/IP split that says what travels to which partner tier, and the resolution of the decommissioned-asset question. Child beats: Define — write the standardized ISD kit pick-list and the content/IP shareable-vs-proprietary split. Develop — resolve deploy-to-sites vs. pull-to-HLC on decommissioned assets; produce the 7F Users Group request deck. Pilot — equip the first non-Houston district against the standard spec. Sustain — the spec becomes the default; new districts buy or receive to it. Near-term ORiON actions: get the fall cohort's EHS/safety content into Xyleme (live gap — Amatrol carries only LION, nothing on confined space; ~70% confidence, Juan's 27 instructor-led hours as the Sept fallback; due Sept 1).

# PILLAR 3 — DELIVERY MODEL

What this covers: How a cohort actually runs, start to finish — the operating model that ties content, instructors, and equipment into a repeatable nine-month program a district can plan around.

Where it stands: The fall 2027 model is largely settled from the CTE scheduling session, and it's being treated correctly as a prototype — Jim set the expectation in the room that it will not run clean, and that only the May completion matters externally.

### The plan — the operating model

- Pacing: 183 total hours September to May, 155 of them on turbine training (against 254 for the standard five-week class). Roughly a ten-minute changeover between blocks.

- Facility rotation (2027): The 6B becomes the CTE unit from January 2027, student use February through May. Five-week craft classes shift to the 7E; ELT moves to the HA.

- Scheduling discipline: Andrew gets dates and lab occupancy, not hour-by-hour. Lab double-booking is expected and acceptable; conflicts get resolved instructor-to-instructor. Roy and Zed coordinate CTE hands-on directly without routing through Andrew.

- Prerequisite gate: Amatrol module plus ten-question assessment before every hands-on block. This is the quality control that lets the model travel.

- Student flow: withdrawal and removal procedures being built jointly with districts (HLC side already drafted); transportation vendor background-check policy started.

The scaling target: roughly 80 to 90 completions a year to match attrition.

ACTION PLAN ITEM Stand Up the National CTE Delivery Model Owner: Linda. The repeatable nine-month operating model a district can plan around — the standardized 2-week-at-district structure, the Amatrol-plus-assessment prerequisite gate, the pacing, and the student-flow procedures. The fall 2027 cohort is the prototype that proves it; only the May completion matters externally. Child beats: Define — lock the pacing, the facility rotation, and the prerequisite gate for the prototype cohort. Develop — build the student-flow procedures (withdrawal/removal with districts) and the scheduling discipline. Pilot — run the fall 2027 cohort as the prototype; expect it to be bumpy. Sustain — capture what held and what didn't; turn the model into the standard a new district adopts. Near-term ORiON actions: confirm the 6B reserved for CTE Feb–May 2027 with Andrew; deliver the CTE lab/equipment schedule to Andrew; confirm Andrew's sign-off before the 2027 baseline locks (his awareness is the scheduling risk, not the plan); confirm the transportation vendor background-check policy; finish the mid-year withdrawal/removal procedure with districts.

# PILLAR 4 — IBC (INDUSTRY-BASED CERTIFICATION)

What this covers: Standing up GE Vernova as a SACA-certifying body for a Heavy Duty Turbine Mechanic credential. This is the lever that turns a budget-dependent program into a self-sustaining one, which is why it's its own pillar and not a footnote.

Where it stands: A 12-to-18-month roadmap, modeled on the Meta data-technician certification. Cal wants a dedicated call on it. Both Cal and Jim V see certification as the durable win — the thing that makes the whole national play permanent rather than grant-cycle-dependent.

### Why it matters

- Unlocks grant funding. Districts and workforce programs can fund a program that leads to a real, portable certification in ways they can't fund generic training.

- Makes the pipeline self-sustaining. Testing and credentialing fees become a revenue source (see Pillar 5).

- It's extendable. The same certifying-body infrastructure works beyond turbine mechanic: steam, generator, nuclear. Build it once, apply it across the disciplines.

ACTION PLAN ITEM Establish the SACA Heavy Duty Turbine Mechanic Certification Owner: Linda / Jim. GE Vernova stood up as a SACA-certifying body for a recognized Heavy Duty Turbine Mechanic credential, modeled on the Meta data-technician cert. The 12-to-18-month build-the-institution effort that unlocks grant funding and the self-sustaining revenue model. Child beats: Define — hold the certification strategy call with Cal; produce the 12–18 month IBC roadmap. Develop — formalize the SACA relationship; define the credential and map it to the curriculum. Pilot — scope and stand up testing labs at partner locations (unscoped, on the critical path for local credentialing); credential the first cohort. Sustain — run the credentialing operation; extend the certifying-body model to steam, generator, nuclear. Near-term ORiON actions: schedule and prep the certification strategy call Cal asked for.

# PILLAR 5 — SELF-FUNDING (FOLLOW THE MONEY)

What this covers: Where every dollar comes from and goes. This pillar is written for leadership. It answers the question Cal and Jim V will ask first: if we're not funding this out of training budget forever, who is paying, and does it actually cover itself?

Where it stands: The self-funding thesis is agreed in principle — grants offset build costs, testing and credentialing fees fund ongoing operations. What's missing is the itemized picture. This section structures it so it can be totaled and defended.

### The cost-avoidance case

- A non-CTE hire costs roughly $23/hour for ~300 hours of training, plus ~$100/day per diem.

- A local CTE cohort avoids that entire cost — the student arrives already trained.

- A national CTE cohort saves roughly three weeks of salary and per diem per student.

- Conservative saving is about $4,260 per student minimum; Jim V's read is closer to $6,000–$7,000.

- At 80–90 students a year, that's a $340K–$630K annual cost avoidance at the conservative end, before any revenue.

### The money model — structured as line items

| Source | Type | Who pays | Covers | Status |
| --- | --- | --- | --- | --- |
| District / ISD funding | Contribution | School districts | Student seats, local delivery | Live — 18 students Sept 1 |
| Grants (workforce / CTE) | Contribution | Grant programs | Build cost, equipment, testing labs | Unlocked by certification |
| Testing & credentialing fees | Revenue | Students / districts / employers | Ongoing certification ops | Future — depends on IBC |
| OFS Training budget | Internal | GE Vernova | The gap not covered above | To be minimized |
| Cost avoidance | Savings | N/A | Offsets internal spend on the P&L | ~$340K–$630K/yr at scale |
| Corporate (Tier 1) | Contribution | Employers like NRG | Possible funding, hiring commitments | Exploratory |

The self-funding argument in one line: grants (unlocked by certification) cover the build; credentialing fees cover operations; district funding covers seats; cost avoidance offsets whatever internal spend remains — so OFS Training's net exposure shrinks toward zero as the model scales.

ACTION PLAN ITEM Build the National CTE Funding & Self-Sustaining Model Owner: Linda / Finance. The itemized money picture for leadership — every source, amount, payer, and status, totaled — that proves the program pays for itself as it scales. Child beats: Define — build the itemized funding model (the line-item table above, made real with numbers). Develop — map the grant landscape the SACA credential unlocks; model the credentialing-fee revenue (fee per test, volume, run rate). Pilot — validate the model against the first funded cohorts (the 18 district-funded students are the first live data point). Sustain — keep the model current as a living picture; it's what the leadership conversation and the module both read from. Near-term ORiON actions: pull the cost-avoidance numbers into the tracker's Hours-Saved / cost-avoidance field where they have a native home.

# THE SIX ACTION PLAN ITEMS, COLLECTED

For the review chain. Six program-sized AP items, one per pillar (two for Pillar 2, which carries both the instructor and equipment programs). Each is a multi-month effort with a single lead and a Define / Develop / Pilot / Sustain child arc. The near-term small stuff lives as children or ORiON actions under these, not as its own AP row.

| # | Action Plan item | Pillar | Lead | Bucket |
| --- | --- | --- | --- | --- |
| 1 | Formalize the CTE Partnership & Tier Framework | Partnerships | Linda | Programs |
| 2 | Build the National CTE Instructor Capacity Model | How We Do It | Linda / Harry | Programs |
| 3 | Develop the Standardized ISD Equipment & Content Program | How We Do It | Linda / Roy | Programs |
| 4 | Stand Up the National CTE Delivery Model | Delivery | Linda | Programs |
| 5 | Establish the SACA Heavy Duty Turbine Mechanic Certification | IBC | Linda / Jim | Programs |
| 6 | Build the National CTE Funding & Self-Sustaining Model | Self-Funding | Linda / Finance | Programs |

Note on bucket: there is no CTE bucket in the tracker today, so these land under Programs unless a CTE bucket is created. Set priority through the tracker's own fields (SQDCG, status) when these go in.

## OPEN QUESTIONS CARRIED INTO THE PLAN

Not blockers, but unresolved, and the plan touches each:

- Is legal support Stephen or someone from legal who works with Alvaro on commercial projects? (Gates every partner agreement.)

- Decommissioned assets deployed to external sites, or pulled back to HLC? (Cal skeptical; affects the stranded-asset method.)

- Does the EHS content actually port to Xyleme by Sept 1, or does the Juan fallback fire?

- How do testing labs get stood up and resourced at partner locations? (Unscoped, on the IBC critical path.)

This framework is a working plan built from the summer cohort results and the CTE program discussions through August 24, 2026. It replaces the July 10 four-bucket doc. Update decisions in place and date them. Structural questions go to Jim.