## OFS Training Action Plan Tracke
AP# | Improvement | Lead | Assist | Owner | Bucket | Description | No Report out at this level | Start | Standard Duration
AP-0733 | XXX Training Development | PLL | Program Mgr | James Rosen | Content Development | See Course Development RACI for more info
AP-0733-1 | XXX Training Analysis - target audience, competencies/objectives, what goals to reach | Program Mgr | PLL | James Rosen | Content Development | Develop/Review List of XXX Training Competencies & identify which should be included in training program | X
AP-0733-2 | Ensure XXX competencies are reflected in Kahuna (internal training only) | Program Mgr | Kahuna Team | Michele Alcantar | Competencies | Review/update existing and/or create new. -Ensure Competency Assessment method is defined for each (training class vs. job-site evaluation) -Confirm which role(s) the competencies belong to
AP-0733-2-1 | Develop XXX Competency Map | Program Mgr |  | Michele Alcantar | Competencies | Create a framework for the competency map & list out competencies & get them reviewed with SMEs. | X | After -1 | varies by scope
AP-0733-2-2 | Develop XXX Import Files | Program Mgr |  | Michele Alcantar | Competencies | Transfer competency maps into Import files that are acceptable for upload in Kahuna. | X | After -2-1 | 1 month after start
AP-0733-2-3 | Import XXX Competency Map Structure in Kahuna | Kahuna Mgr. |  | Michele Alcantar | Competencies | Use Import file from Program Manager to load Map structure into Kahuna | X | After -2-2 | 1 month after start
AP-0733-2-4 | Data Mine and Validate XXX User Data for Baselining | Program Mgr | Kahuna Mgr/ TDM | Michele Alcantar | Competencies | TPM to work with Kahuna Mgr to create the data-sheet of relevant affected employees for reviewing/validation. TPM to work with TDMs to review/validate the data-sheet that will then be used for baselining activities | X | After -2-2 | 1 month after start
AP-0733-2-5 | Configure Kahuna for XXX Competency Map & Baseline & Load User Assignments in Kahuna | Kahuna Mgr | Program Mgr | Michele Alcantar | Competencies | Use Baselining data from Program Manager to load user assignments in Kahuna | X | After -2-4 | 1 month after start
AP-0733-2-6 | Rollout XXX Comms Plan | Kahuna Mgr | Program Mgr | Michele Alcantar | Competencies | Communicate new/updated maps & required actions to stakeholders | X | After -2-4 | 1 month after start
AP-0733-3 | XXX Training Design & Content Assembly | Program Mgr | PLL, D&D | James Rosen | Content Development | Initial Design & content gathering | X
AP-0733-3-1 | Overall XXX Design | Program Mgr | PLL, D&D | James Rosen | Content Development | -Select Delivery Modalities (ILT, Lab, WBT, Quiz/test) -Develop Learning Objectives -High Level Lessons Storyboard/Course Overview | X
AP-0733-3-2 | XXX Instructor Identification | PLL |  | James Rosen | Content Development | Identify target instructor(s) for pilot/future sessions (cross training needs) | X
AP-0733-3-3 | XXX Storyboard & Content Gathering | Program Mgr | PLL, D&D | James Rosen | Content Development | -Detailed Storyboard -Build Quizzes/Tests/Labs -Gather/Identify needed media | X
AP-0733-3-4 | Build XXX Media | D&D | PLL, PM | James Rosen | Content Development | i.e. 3D models, videos, etc. | X
AP-0733-4 | Load XXX Training course into our relevant systems (Xyleme, Outline Tool, LMS, Scheduling Tool, etc.) | PLL | Program Mgr, D&D | James Rosen | Content Development | Load into Xyleme, Outline tool, downstream systems/etc.
AP-0733-4-1 | Finalize XXX Storyboard | PLL | D&D | James Rosen | Content Development | Approve Storyboard, assemble Box folder & initiate Xyleme request | X
AP-0733-4-2 | Finalize XXX materials in Xyleme | D&D | PLL | James Rosen | Content Development | Create the final formatted tools, slides, manuals, videos, etc in Xyleme. -Approve final Xyleme package | X
AP-0733-4-3 | Load XXX Course Outline | PLL |  | James Rosen | Content Development | Load Course Outline (feeds LMS, catalog, Blueprint/quoting tools, Kahuna instructor competencies, etc.) | X
AP-0733-5 | Deliver XXX Training Pilot session (if applicable) | PLL | Program Mgr | James Rosen | Content Development | Deliver pilot session and review initial feedback

## Comments
Row 79 | 01082025 find SME. Ask Tam for I&C | Luca Martino | 01/09/25 3:53 AM
Row 93 | 01082025 Mike to send me list of SME | Luca Martino | 01/09/25 3:53 AM
Row 128 | 01082025 Mike is working with CICB for this. Waiting quotation for TTT and be instructors in Houston LC - instructors need to have master level | Luca Martino | 01/09/25 3:53 AM
Row 129 | 01082025 on hold because you can only do it in Massachussetts | Luca Martino | 01/09/25 3:54 AM
Row 130 | 01082025 include corporate aspects. Talk with the communication team (Lindsay Savage) | Luca Martino | 01/09/25 3:54 AM
Row 258 | Include Jimmy Cahill. Then 1. collect data from Mike and Kelly on competencies - 2. define list of SMEs - 3. define workout dates and location | Luca Martino | 01/09/25 11:00 AM
Row 291 | From Pixaera to normal WBT - Quality expectation is end of June | Luca Martino | 03/27/25 11:15 AM
Row 446 | 01082025 review the content to match the need (that must be defined) - create a lab for intermediate and advanced | Luca Martino | 01/09/25 3:51 AM
Row 447 | 01082025 all in Kahuna Integration GE Star box folder. It is with Kelly | Luca Martino | 01/09/25 3:51 AM
Row 453 | 01082025 (Salim & Beau) to incorporate in the bolting training - create document for recertification | Luca Martino | 01/09/25 3:52 AM
Row 454 | in the box from Mike | Luca Martino | 01/09/25 3:52 AM